## Example
Example of project plan based on milestones
[7 empty] | First year of funding | [11 empty] | Second year of funding
# | Title | Description | Category overall goal | Proof for fulfillment and/or KPIs demonstrating successful implementation | Start | End | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Recruiting
1 | Recruitment of data journalist Note: The planned recruitment of new staff must be integrated into the project milestones and must not delay the project start, which should occur no later than two months after the funding / financing has been approved. | Lorem ipsum dolor sit amet, consectetuer adipiscing elit. Aenean commodo ligula eget dolor. Aenean massa. | Strengthening the impact of our journalistic work | Example: Evidence: employment contract | Start: 2025-02-01; End: 2025-04-01
2 | Recruitment of product developer | Lorem ipsum dolor sit amet, consectetuer adipiscing elit. Aenean commodo ligula eget dolor. Aenean massa. | Strengthening our economic sustainability | Lorem ipsum dolor sit amet, consectetuer adipiscing elit. | Start: 2025-09-01; End: 2025-10-01
Increasing reach | bar: First year of funding Apr
3 | Offenes Diskussionsforum als regelmäßiges, analoges Veranstaltungsformat gelauncht | Lorem ipsum dolor sit amet, consectetuer adipiscing elit. Aenean commodo ligula eget dolor. Aenean massa. | Strengthening our economic sustainability | Example: Evidence: Number of participants, photos of the discussion forum KPI: Number of participants Forum 1: 20–30 participants Forum 2: 30–40 participants Forum 3: stable, at least 40 participants Forum 4: stable, at least 40 participants | Start: 2025-06-01; End: 2025-07-01
Strategic planning
4 | Internal strategy workshop on planning targets for 2026 | Lorem ipsum dolor sit amet, consectetuer adipiscing elit. Aenean commodo ligula eget dolor. Aenean massa. | Strengthening our operational resilience | Lorem ipsum dolor sit amet, consectetuer adipiscing elit. | Start: 2026-01-01; End: 2026-01-01
Training
5 | Training on TikTok | Lorem ipsum dolor sit amet, consectetuer adipiscing elit. Aenean commodo ligula eget dolor. Aenean massa. | Strengthening the impact of our journalistic work | Lorem ipsum dolor sit amet, consectetuer adipiscing elit. | Start: 2026-04-01; End: 2026-04-01
Expert consultation
6 | External consulting and workshop to establish an error culture in the editorial office | Lorem ipsum dolor sit amet, consectetuer adipiscing elit. Aenean commodo ligula eget dolor. Aenean massa. | Strengthening the impact of our journalistic work | Lorem ipsum dolor sit amet, consectetuer adipiscing elit. | Start: 2025-12-01; End: 2025-12-01